## README
Issue Intake Log Workbook
Purpose | Captures data, reporting, access, metadata, and workflow issues in a structured way so they can be triaged, assigned, remediated, and monitored.
How to use | Log material issues, assign severity and owner, document remediation, and track recurrence and closure.
Governance rule | Repeated, material, or cross-team issues should not be handled through informal email only; they should be logged and tracked.

## Issue Log
Issue ID | Date Identified | Reported By | Category | Affected Asset / Report / System | Issue Summary | Quality Dimension | Severity | Business Impact | Output Use Status | Assigned Owner | Supporting Role | Target Resolution Date | Status | Root Cause Category | Remediation Action | Validation Status | Closure Date | Recurrence | Related Change ID | Notes
ISS-001 | 2026-01-12 | N. Adams | Data Quality | Executive KPI Dashboard | KPI total did not reconcile to certified reporting mart | Consistency | High | Management reporting confidence affected | Pause Release | Reporting Data Owner | Reporting Steward | 2026-01-15 | In Remediation | Transformation logic defect | Correct mapping logic and revalidate downstream totals | Pending |  | No | CHG-004 | Escalated due to dashboard visibility
ISS-002 | 2026-01-20 | L. Brown | Metadata | Business Glossary | Two teams used conflicting definitions for Active Customer | Consistency | Medium | Comparability risk across reporting outputs | Continue With Caveat | Customer Data Owner | Customer Steward | 2026-01-27 | Assigned | Business rule ambiguity | Approve single definition and update glossary | Pending |  | Yes | CHG-006 | Requires owner decision
ISS-003 | 2026-02-01 | P. Chen | Access | Customer Detail Extract | Broad export request granted without documented rationale | Integrity | High | Sensitive data exposure risk | Stop Use | Customer Data Owner | Governance Lead | 2026-02-03 | In Triage | Access workflow breakdown | Review access decision and implement stronger logging | Pending |  | No |  | Potential policy exception
ISS-004 | 2026-02-11 | R. Singh | Workflow | Monthly Reporting Process | Manual adjustment file not version-controlled and approver unclear | Accuracy | Medium | Auditability and release confidence weakened | Continue With Caveat | Reporting Manager | Reporting Steward | 2026-02-18 | Open | Documentation gap | Introduce change notice and traceability requirement | Pending |  | Yes | CHG-009 | Linked to recurring month-end pressure

## Lists
Severity | Status | Category | Dimension | Output Use Status | Recurrence